## Schedule
|  |  | Mini-Schedule Planned VS Actual QTY | [41 empty] | This Excel sheet was prepared by Hany Ismael - PlanningEngineer.Net
|  |  | 2021-07-30 |  | 2021-08-06 |  | 2021-08-13 |  | 2021-08-20 |  | 2021-08-27 |  | 2021-09-03 |  | 2021-09-10 |  | 2021-09-17 |  | 2021-09-24 |  | 2021-10-01 |  | 2021-10-08 |  | 2021-10-15 |  | 2021-10-22 |  | 2021-10-29 |  | 2021-11-05 |  | 2021-11-12 |  | 2021-11-19 |  | 2021-11-26 |  | 2021-12-03 |  | 2021-12-10 |  | Total Actual | Total Planned |  | www.PlanningEngineer.Net
Activity ID | Activity Name | Unit | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned
Column Labels
|  |  | 2021-07-30 |  | 2021-08-06 |  | 2021-08-13 |  | 2021-08-20 |  | 2021-08-27 |  | 2021-09-03 |  | 2021-09-10 |  | 2021-09-17 |  | 2021-09-24 |  | 2021-10-01 |  | 2021-10-08 |  | 2021-10-15 |  | 2021-10-22 |  | 2021-10-29 |  | 2021-11-05 |  | 2021-11-12 |  | 2021-11-19 |  | 2021-11-26 |  | 2021-12-03 |  | 2021-12-10 |  | Total Sum of Actuals.Actual QTY | Total Sum of Weekly QTY
Row Labels | Activity Name | Unit | Sum of Actuals.Actual QTY | Sum of Weekly QTY | Sum of Actuals.Actual QTY | Sum of Weekly QTY | Sum of Actuals.Actual QTY | Sum of Weekly QTY | Sum of Actuals.Actual QTY | Sum of Weekly QTY | Sum of Actuals.Actual QTY | Sum of Weekly QTY | Sum of Actuals.Actual QTY | Sum of Weekly QTY | Sum of Actuals.Actual QTY | Sum of Weekly QTY | Sum of Actuals.Actual QTY | Sum of Weekly QTY | Sum of Actuals.Actual QTY | Sum of Weekly QTY | Sum of Actuals.Actual QTY | Sum of Weekly QTY | Sum of Actuals.Actual QTY | Sum of Weekly QTY | Sum of Actuals.Actual QTY | Sum of Weekly QTY | Sum of Actuals.Actual QTY | Sum of Weekly QTY | Sum of Actuals.Actual QTY | Sum of Weekly QTY | Sum of Actuals.Actual QTY | Sum of Weekly QTY | Sum of Actuals.Actual QTY | Sum of Weekly QTY | Sum of Actuals.Actual QTY | Sum of Weekly QTY | Sum of Actuals.Actual QTY | Sum of Weekly QTY | Sum of Actuals.Actual QTY | Sum of Weekly QTY | Sum of Actuals.Actual QTY | Sum of Weekly QTY
Project
Building 1
Zone 1
J38-WH1-Z1-M155 | Activity 1 | L.M | 5 | 66.6667 | 10 | 33.3333 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 15 | 100
Zone 2
J38-WH1-Z2-M155 | Activity 1 | L.M |  | 0 |  | 11.1111 | 10 | 8.8889 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | 20
Zone 3
J38-WH1-Z3-M155 | Activity 1 | L.M |  | 0 |  | 0 |  | 18 |  | 12 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 30
Zone 4
J38-WH1-Z4-M155 | Activity 1 | L.M |  | 0 |  | 0 |  | 0 |  | 21 |  | 14 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 35
Grand Total |  |  | 5 | 66.6667 | 10 | 44.4444 | 10 | 26.8889 |  | 33 |  | 14 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 25 | 185
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Week Ends
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Data
Activity ID | Activity Name | Project Name | Building Name | Zone | Div of work | QTY | Unit | Planned Start | Planned Finish
J38-WH1-Z1-M155 | Activity 1 | Project | Building 1 | Zone 1 | Div 1 | 100 | L.M | 2021-07-22 | 2021-08-01
J38-WH1-Z2-M155 | Activity 1 | Project | Building 1 | Zone 2 | Div 1 | 20 | L.M | 2021-07-29 | 2021-08-08
J38-WH1-Z3-M155 | Activity 1 | Project | Building 1 | Zone 3 | Div 2 | 30 | L.M | 2021-08-05 | 2021-08-15
J38-WH1-Z4-M155 | Activity 1 | Project | Building 1 | Zone 4 | Div 2 | 35 | L.M | 2021-08-12 | 2021-08-22
J38-WH2-Z1-M155 | Activity 1 | Project | Building 2 | Zone 1 | Div 1 | 40 | L.M | 2021-08-19 | 2021-08-29
J38-WH2-Z2-M155 | Activity 1 | Project | Building 2 | Zone 2 | Div 1 | 25 | L.M | 2021-08-26 | 2021-09-05
J38-WH2-Z3-M155 | Activity 1 | Project | Building 2 | Zone 3 | Div 2 | 15 | L.M | 2021-09-02 | 2021-09-12
J38-WH2-Z4-M155 | Activity 1 | Project | Building 2 | Zone 4 | Div 2 | 10 | L.M | 2021-09-09 | 2021-09-19
J38-WOS-GN-M155 | Activity 1 | Project | Building 3 | All | Div 3 | 60 | L.M | 2021-09-16 | 2021-09-26
J38-WOS-GN-M156 | Activity 2 | Project | Building 3 | All | Div 3 | 60 | M2 | 2021-09-23 | 2021-10-03
Formulas:
Planned Finish = [Planned Start]+10
Planned Start = [Planned Start, row above]+7

## Actuals
Activity ID | Week Number | Actual QTY
J38-WH1-Z1-M155 | WK01 | 5
J38-WH1-Z1-M155 | WK02 | 10
J38-WH1-Z2-M155 | WK03 | 10
J38-WH2-Z1-M155 | WK02 | 25

## weeks_dist
|  |  |  | WK01 | WK02 | WK03 | WK04 | WK05 | WK06 | WK07 | WK08 | WK09 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20
|  |  | 2021-07-17 | 2021-07-24 | 2021-07-31 | 2021-08-07 | 2021-08-14 | 2021-08-21 | 2021-08-28 | 2021-09-04 | 2021-09-11 | 2021-09-18 | 2021-09-25 | 2021-10-02 | 2021-10-09 | 2021-10-16 | 2021-10-23 | 2021-10-30 | 2021-11-06 | 2021-11-13 | 2021-11-20 | 2021-11-27 | 2021-12-04 | Check
Activity ID | Planned Start | Planned Finish | Working Days | WK01 | WK02 | WK03 | WK04 | WK05 | WK06 | WK07 | WK08 | WK09 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20
J38-WH1-Z1-M155 | 2021-07-22 | 2021-08-01 | 8 | 25% | 75% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
J38-WH1-Z2-M155 | 2021-07-29 | 2021-08-08 | 8 | 0% | 25% | 62.5% | 12.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
J38-WH1-Z3-M155 | 2021-08-05 | 2021-08-15 | 9 | 0% | 0% | 22.22% | 66.67% | 11.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
J38-WH1-Z4-M155 | 2021-08-12 | 2021-08-22 | 9 | 0% | 0% | 0% | 22.22% | 66.67% | 11.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
J38-WH2-Z1-M155 | 2021-08-19 | 2021-08-29 | 9 | 0% | 0% | 0% | 0% | 22.22% | 66.67% | 11.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
J38-WH2-Z2-M155 | 2021-08-26 | 2021-09-05 | 9 | 0% | 0% | 0% | 0% | 0% | 22.22% | 66.67% | 11.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
J38-WH2-Z3-M155 | 2021-09-02 | 2021-09-12 | 9 | 0% | 0% | 0% | 0% | 0% | 0% | 22.22% | 66.67% | 11.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
J38-WH2-Z4-M155 | 2021-09-09 | 2021-09-19 | 9 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 22.22% | 66.67% | 11.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
J38-WOS-GN-M155 | 2021-09-16 | 2021-09-26 | 9 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 22.22% | 66.67% | 11.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
J38-WOS-GN-M156 | 2021-09-23 | 2021-10-03 | 9 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 22.22% | 66.67% | 11.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Formulas:
Planned Start = VLOOKUP([Activity ID],Data!A:J,9,FALSE)
Planned Finish = VLOOKUP([Activity ID],Data!A:J,10,FALSE)
Working Days = NETWORKDAYS.INTL(weeks_dist[[#This Row],[Planned Start]],weeks_dist[[#This Row],[Planned Finish]],Settings!$H1,Settings!$L:$L)

## Settings
1 | Week Start Day | Saturday | 16 | Week End (Holiday) | Friday | 16 | Holidays
2021-08-01
2021-07-30

## Calculations_Dont_Change
Week Start Day |  | Week End
Saturday | 16 | Friday | 16 | Week | Date
Sunday | 17 | Saturday | 17 | WK01 | 2021-07-23
Monday | 2 | Friday & Saturday | 7 | WK02 | 2021-07-30
|  |  |  | WK03 | 2021-08-06
|  |  |  | WK04 | 2021-08-13
|  |  |  | WK05 | 2021-08-20
|  |  |  | WK06 | 2021-08-27
|  |  |  | WK07 | 2021-09-03
|  |  |  | WK08 | 2021-09-10
|  |  |  | WK09 | 2021-09-17
|  |  |  | WK10 | 2021-09-24
|  |  |  | WK11 | 2021-10-01
|  |  |  | WK12 | 2021-10-08
|  |  |  | WK13 | 2021-10-15
|  |  |  | WK14 | 2021-10-22
|  |  |  | WK15 | 2021-10-29
|  |  |  | WK16 | 2021-11-05
|  |  |  | WK17 | 2021-11-12
|  |  |  | WK18 | 2021-11-19
|  |  |  | WK19 | 2021-11-26
|  |  |  | WK20 | 2021-12-03